## Project schedule
Project schedule template
Stage ID | Stage | Involved | Tools/Sources of assistance | Lead | Support | Estimated timelines | Completed? | Start date | Completion date
1 | Scoping the bigger picture | Theory of change/Target & goal setting/definition of KPIs |  |  |  | 3-5 days
2 | Requirements | Define what is required for user functionality, processes & reporting involving staff at all levels/roles in the organisation & ideally service users for a 365 view of what's needed. Ranking of requirements into Essential/Desirable/Aspirational |  |  |  | 3-4 days
3 | Data clean up/consolidation | Implementation lead in conjunction with data owners - important step as helps establish what data is vital/what can be standardised in terms of pick lists etc. |  |  |  | 4-5 days
4 | Vendor selection | Source and review the functionality of possible vendor solutions in light of the requirements |  |  |  | 1-2 days
5 | System design/customisation | Design or customise template. Fields, relationships, picklists, automation, links to other systems etc. Write test scripts from the requirements/user stories/customer journeys |  |  |  | 3-4 days for light touch CRM customisation/several weeks for more complex customisation/design
6 | Testing | Execute test scripts |  |  |  | 1-2 days
7 | Data migration | Ensure data is in the right format & then import |  |  |  | 1-2 days
8 | User/Security set up | Set up users with their correct security/functionality permissions |  |  |  | 1-2 days
9 | Testing | Execute test scripts |  |  |  | 1-2 days
10 | Customisation | Adapt and refine system where required |  |  |  | 1-2 days
11 | Rework process/guidelines documentation | Rewrite all internal process documentation to include new system eg new staff onboarding/exit process, changes to service user interaction/recording, reporting guidelines etc. |  |  |  | 4-5 days
12 | Training | Develop training materials - quick cards, videos, how to guides, Q&A etc |  |  |  | 5-6 days
13 | Support & ongoing training set up | Develop support materials & mechanisms for reporting problems etc. |  |  |  | 2-3 days
14 | Go live | Shutting off access to old systems/archiving of old databases/ensuring all links on websites, user platforms lead to the new system/ensuring all is running smoothly |  |  |  | 1-2 days
15 | Maintenance & Support | Upgrades, ongoing training for new functionality & new staff members, end user support |  |  |  | Ongoing
16 | Continuous Improvement |  |  |  |  | Ongoing