## Risks & challenges
Risks & challenges template
Potential risk or challenge | What does that mean? | How can you mitigate against it?
Growing complexity | As you start implementing a new database package everyone will begin to realise the potential and functionality requests will start to increase and costs/time invested can spiral with them. | Clearly define and continually redefine what the core goals are. Assess each requirement on how much time it would save or how much better it would make your service provision for your users. Get stakeholders to upvote requirements they back.
Limitations on what's possible | Time, cost, technical viability, vendor agreement etc. can all limit what you're hoping to achieve in terms of functionality | Set expecations. No single software solution or database package can be expected to do everything for everyone
Increasing data volumes | The amount of data you store in your database will naturally increase over time this can impact on licencing & storage costs and can impact on data processing speed. | Do you need to be storing all the data you are? Do you need to keep it for so long? Could you archive it outside of the live system so it can be referrenced but not edited?
Growing team numbers | More people needing to access the database can increase licencing costs and the amount of time spent on system administration and training | Are there licences from previous staff which can be reallocated to new staff? Does the vendor offer training which staff can join? Are there alternatives to 1 to 1 training eg group sessions, videos etc.
Maintaining data integrity & security | Pulling more and more data into one places from different sources, having more people interact with data | Draw up tight guidelines for user access & data storage. For example, onboarding and particularly offboarding processes should include steps around database access.
Enforcing data retention guidelines | As an organisation your data protection strategy should include timelines on how long different types of data are kept. How will you enforce this in the system? | The optimum solution is that you system has built in data